## Sheet1
For a simple task - a grant to buy equipment for the club/group/association
Stage | Tasks | Responsible | Week 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Find grants available | Determine priorities | Committee | bar: Week 1 to 2
| Gain committee approval | Committee | bar: 3
Write Grant | Get quotes | Secretary | bar: 4 to 6
| Write application | Secretary/Treasurer | bar: 4 to 6
Submit Grant by deadline | bar: 6
Wait on decision
If funded
| Receive funds | Committee
| Check quotes are still valid | Secretary
| Buy equipment | Treasurer
| Copy receipts | Treasurer
| Write acquittal (with photos) | Secretary
| Submit acquittal report | Secretary/Treasurer